## Sheet1
XXXX UPGRADE Project Release Criteria |  |  |  | Status at: | DD/MM/YYYY | Prepared by: xxxxxxxxxxxx yyyyyyyyyy
|  |  |  | Version: | 0.3
Version History
| No | Acceptance Criteria | Complete Y/N | Target date for completion (DATE & RAG) | Associated risks that have not been mitigated (Detail and RAG) | Comments / Follow on actions (state action, who & when) | SharePoint Link (For all documents / For software, library reference where stored) | Receiver Sign-off (Inf Services, Risk and Audit,QA, Arch & Security) Y/N | Version No | Date | Who | Comments
[9 empty] | 0.1 | 23/5/2012 | IM | Initial Draft
| E1 | Example : Signed of Project Charter | Y | 21/5/2010 | PCI out of scope, mitigation plan developed | xx/xx Lersos undertaken audit, see Acceptance Criteria XX,PCI | http://xxxportal/Projects/upgrade/SitePages/Home.aspx | David Jones | 0.2 | 26/5/2012 | IM | Additional Criteria
[9 empty] | 0.3 | 27/5/2012 | IM | Comms Criteria and document approval matrix
| 1 | Detailed requirements specification
| 2 | Signed off high level and detailed technical design documentation, diagrams and inventory
| 3 | Facilities Design Documentation
| 4 | Service Design and Service Level Documentation and agreed service measures in place and proven
| 5 | Operational level agreements and underpinning contracts with supplier's, maintained agreements: - IBM - Oracle - FPIS - Security products - Other's
| 6 | Capacity plan (for system as a whole and individual components, detailing upgrade points / triggers)
| 7 | All non Production network access points closed
| 8 | All build / UAT / default passwords changed
| 9 | All non Production staff removed
| 10 | All remote access points review, documented and agreed by Production team (remote access only to be provide for period of requirment, not as a default | [6 empty] | Document Approval matrix
| 11 | Strategy for software and components upgrades | [6 empty] | Name | Job Title | Date | Comments
| 12 | Documented whole system build guide(s) | [6 empty] | xxx | Head of IS
| 13 | Documented, scenario tested backup and restore process | [6 empty] | xxx | Head of QA
| 14 | Documented risk analysis on new system and environment, highlighting all know exposures with mitigations / counter measures | [6 empty] | xxx | Head of Systems Dev
| 15 | Software Licenses detail (users, renewal, limitations, payment details) | [6 empty] | xxx | Head of Arch & Security
| 16 | Have all the Stakeholders / customers ben entered into the CMS with contact dedails (email / telepone) and escalation path's | [6 empty] | xxx | PM ITIL Programme
[9 empty] | xxx | xxx
| 17 | Populated Configuration Database / Baseline - Hardware - Software -Network details (Firewalls) - all Documents (mapped to SharePoint) | [6 empty] | Bussiness Owner?
| 18 | Documented Intergration and UAT release builds and change records | [6 empty] | Document Consulted / Informed matrix
| 19 | Documented Production release build and change records | [6 empty] | Name | Job Title | Date | Comments
| 20 | Software Library (all base media, duplicated over two sites) | [7 empty] | Head of PMO
| 21 | Documented housekeeping processes | [7 empty] | PM Prog Ignite
| 22 | Housekeeping calendar
| 23 | PCI Certification
| 24 | Penetration tests complete and exposures managed
| 25 | xxx Application Penetration Testing received and exposures understood |  |  |  | 26/5 Requested
| 26 | Audit processes, logs, reports and management controls
| 27 | All security checks been completed and sucessfuly signed off
| 28 | Documented Security processes and procedures -Data Centre Environment
| 29 | Documented Security processes and procedures -System, application and database - Password hierarchy - Audit process
| 30 | BT Confirmation that there are two independent routes into the data centre with no single points of failure
| 31 | Matrix showing all password access levels and whom handed over to Security and IT Security Team
| 32 | All individuals with access to the system advised should they must use the Change / Emergency Change Process if they make a change. All changes must be documented
| 33 | Documented results of testing & validation results, detailing all outstanding errors and documented workarounds
| 34 | Post live testing planned and documented
| 35 | Release plan agreed and signed off by all impacted stakeholders
| 36 | Release date communicated and agreed with all parties
| 37 | Proven / documented data migration path with normalization
| 38 | Documented, tested process to retrieve historical data
| 39 | Trained staff on data retrieval (old) from data warehouse
| 40 | Data warehouse established for historical data
| 41 | Trained staff on data retrieval (new) from data warehouse
| 42 | Documented, tested process to retrieve new data
| 43 | Positive Communications Plan
| 44 | Post live testing plan
Tested back out plan
| 45 | Release support in place (including first peak cover)
| 46 | Major incident plan and process
| 47 | Documented early life support during phased handover period
| 48 | Systems guides entered in the knowledge base
| 49 | Software manuals entred in knowledge base
| 50 | 1st & 2nd line support training complete - application - database - network - other
| 51 | 1st & 2nd line support documentation complete
| 52 | Service desk training complete
| 53 | 1st & 2nd line support documentation complete
| 54 | Service desk documentation complete
| 55 | Closure communications Plan
| 56 | Post go live review planned
| 57 | Planed to retire old system
| 58 | Have business managers signed off new release
| 59 | Have IT Operational managers signed off new release
Note on C5: imitchell: See comments of example detail to be included
Note on H5: imitchell: SharePoint link to the document within the Document Centre. Details where the Primary and offsite secondary software is held and maintained.
Note on I5: imitchell: Intials of BAU Team member who has signed-off document / received software etc
Note on C11: imitchell: - Service Level Requirements - Information Security Req - Compliance requirements (BofE, Card Co's, Industry bodies) - Architectural constraints - Migrating requirements (e.g. data to be migrated, history) - Operational requirements (Continuity required, Backup and restore, monitoring and measures tools, capacity, availability, reliability, maintainability documentation, reporting, under pinning contracts / OLA's training and support) Access rights (access levels to support PCI)
Note on C12: imitchell: Documentation and diagram's To include updates and changes made during integration.
Note on C15: imitchell: To include, levels of support, turnaround times, hours of support, escalation processes and procedures etc
Note on C22: imitchell: Confirmation that full rebuild of system (operating system, application. database and components configuration etc) has been undertaken against the guide(s) by 2nd line support), controlled builds.
Note on C23: imitchell: Back-up process cycles to be documented, responsibility assigned, checks established and escalation for failures). Proven restore exercises undertaken. Planned recovery exercises.
Note on C28: imitchell: To be handed over to QA team, resource required to manage going forward! (Issue)
Note on C30: imitchell: Assumed to be a base, clean build not a copy of xxx (inc all components). To be done against build guides by 2nd line staff (not vendor's)
Note on C31: imitchell: All Operating, application, database and configurations, patches etc. Offsite to include Build guides.
Note on C32: imitchell: Including Roles and responsibilities, checks and escalation processes
Note on C36: imitchell: Tom Davidrecommended obtaining
Note on C39: imitchell: Including list of all people authorized to have access today
Note on C40: imitchell: Including list of all people authorized to have access today. Using FIS structure
Note on C44: imitchell: All test plans successfully completed
Note on C45: imitchell: Performance testing Positive confirmation of correct operational behaviour Plan to test all batch jobs and process post go-live
Note on C58: imitchell: When called, by whom after what period, who is engaged, informed and advised. Comms preplanned
Note on C67: imitchell: Thank pilots, early adopters and positive press on enhancements
Note on C69: imitchell: Data archiving, system hardware / software retiring, contract / license cancelation, segregation & removal of network access, closure of gateways, secure wiping of memory, access review to data centre' s, update of configuration database, purge of software libraries and documentation etc